## Slide 1: PINEMAP Executive Committee Meeting Planning for the No-Cost Extension Year
November 19, 2015

## Slide 2: Agenda for Today
No-cost extension update
Focusing on the goals
Final report
  Timing
  Content
DSS name

## Slide 3: 1 year No-cost extension
Request submitted July 29
Approved by NIFA November 2
UF has finished processing most subcontracts
Contact Grace or Tim if you encounter problems

## Slide 4: Focusing on PINEMAP goals
Institutional coordinators: please review and match projected remaining funds to remaining planned tasks
Are there high priority efforts (continuing or new) that do not have sufficient resources to proceed or begin?
Communication is key to finish deliverables on time
Thanks for your continued responsiveness to requests for information

## Slide 5: Focusing on PINEMAP goals
Limited funds at UF are being redistributed to high priority efforts
  Ensuring regional modeling effort can reach full completion
  Cost-sharing effort with Forest Productivity Cooperative to scale Jay Raymond N efficiency work to region
  Focused outreach to minority landowners
Needs assessment for year 3 maintenance and measurements at Tier III sites
Needs assessment for Rh:Ra work
Other goal-focused, high priority work that requires assessment?

## Slide 6: Planning for Final Report
We plan to produce a single additional glossy report as our final report
Timing relative to PINEMAP meeting week of 5/23/2016
  Takes ~4 months to produce
First wave of articles written based on 1st order “big science” integrative papers and meeting presentations, finish review/ editing process late September 2016
Second phase of 7-10 articles based on 2nd order “reflective” integrative paper results and outcome theme results summaries in fall 2016
Goal is to release final report December 2016

## Slide 7: PINEMAP DSS
What is the most appropriate name for this DSS given PINEMAP is almost over?